# Task Management System – Requirements

Oct 26, 2026 · @techDr

## Overview & goals

We are amending our existing task management app so it replaces the office whiteboards and creates, routes and chases work automatically for a digital marketing agency serving doctors, clinics and hospitals.

Today every person's routine, monthly deadline and client request lives on whiteboards. Work stalls when one person waits on another and nobody notices. The system must fix that.

Goals:

- No manual task creation for routine work. Daily, weekly and monthly tasks appear on their own.

- No silent waiting. When a task needs input from someone else, that person is told and reminded until they deliver.

- Automatic handoffs. When one task is done, the next person's task unlocks and they are notified.

- Escalation. Overdue work goes to the Coordinator, then both admins.

- One view for the admins (Abhista & Raviteja) of who is blocked, what is overdue and how each client is doing, plus a read-only board of everyone's tasks that opens without logging in.

Everything the developer needs is in this one doc. The data to import is in tab 5 (Seed Data): 10 people (2 admins and 8 team members), 4 teams and 123 task templates with triggers, dependencies and handoffs already defined.

This is an amendment to the app we already have, not a new build. The developer first compares the app with this document, then adds only what is missing, and the whole change ships in one working day (see Build plan).

How to use this doc, in order:

- Read this tab fully, especially Rules that keep the app from breaking. If anything here is unclear, ask before writing code.

- 2. Cross-Team Dependencies lists every handoff between teams and shows the website flow.

- 3. Task Templates lists every task the system must create.

- 4. Cursor Prompt is what you paste into Cursor, together with all 5 tabs exported as Markdown (the steps are in that tab). 5. Seed Data (JSON) is the data the app imports; it is one of those 5 exports, so nothing outside this doc is needed.

## Team, users & roles

The system has 8 team members in 4 teams plus 2 admins, Abhista and Raviteja; every overdue task escalates first to Shaheena, then to both admins. "Admins" in this doc always means Abhista and Raviteja.

| Person | Team | Role in system | Main work | Escalates to |
| --- | --- | --- | --- | --- |
| Abhista & Raviteja | Management | Admins (both equal) | Approves daily plans, internal website audits, payments, escalations | — |
| Shaheena | Coordination | Coordinator + Content Writer | Client WhatsApp communication, assigning work, website/social/blog content | Admins |
| Gouthami | Marketing | Member | GMB, social media, ads, reports, onboarding | Shaheena → Admins |
| Ayesha | Marketing | Member | GMB, social media, ads, reports, onboarding | Shaheena → Admins |
| Raghu | Website | Member | Website builds, maintenance, appointment booking, SEO | Shaheena → Admins |
| Dileep | Design & Video | Member | Video shoots, video edits & thumbnails | Shaheena → Admins |
| Rohit | Design & Video | Member | Posters, video edits & thumbnails | Shaheena → Admins |
| Bhavya | Design & Video | Member | Posters, animated videos | Shaheena → Admins |
| Chaithanya | Design & Video | Member | Posters, animated videos, ad creatives | Shaheena → Admins |

Permissions:

- Admins (Abhista, Raviteja): see everything, edit templates, approve plans, reassign any task, generate or revoke the public board link. Either admin can approve; both receive escalations.

- Coordinator (Shaheena): sees all teams, creates and assigns tasks, receives first-level escalations.

- Member: sees own tasks and tasks waiting on them, updates status, adds comments and files.

- Public viewer (no login): opens the public board link and sees everyone's tasks read-only. Cannot change anything.

People, teams and roles must be editable from an admin screen, not hard-coded.

## Core concepts

Every template in tab 5 (Seed Data) is a task template; the system turns templates into real task instances, per day, per client or per project.

Task template: the definition (who, what, when, depends on what). Editable by Admin.

Task instance: one actual piece of work, created from a template, with a due date, a client (if any) and a status.

Project template: an ordered chain of templates created together. Example: "New Website Build" creates Raghu's 9 steps plus the content, image and confirmation tasks they wait on.

Client: each client (e.g. Skin NU, New Lotus) gets its own monthly, weekly and per-project tasks.

Trigger types (every template has exactly one):

| Trigger type | Meaning | How the system creates it |
| --- | --- | --- |
| Auto (Scheduled) | Happens on a fixed time, weekday or date | Scheduler creates instances (daily 9:30 AM run, weekly, monthly) |
| Self-Trigger | The same person starts it once their previous step is done | Unlocks when its Depends On tasks are Done |
| Dependent | Cannot start until someone else delivers input | Created as Waiting on Input; unlocks when the linked cross-team task is Done |
| On Event | Starts when something happens (negative review, GMB query, update request) | Created manually or by an event (form, webhook, button) |

Statuses: Locked (dependencies not done) → To Do → In Progress → Waiting on Input → In Review (sent for approval) → Done. Also Cancelled.

Repeat values: Daily (Mon–Sat), Weekly (with weekday), Monthly (with day of month), Quarterly, Per new client, Per new website, Per shoot, Per post/piece, On event, Ongoing.

## Data model

Seven tables cover everything; the seed data in tab 5 maps one-to-one onto TaskTemplate and TemplateDependency.

| Table | Key fields | Notes |
| --- | --- | --- |
| User | id, name, team_id, role (admin / coordinator / member), phone, email, escalates_to_user_id, active | WhatsApp number needed for notifications |
| Team | id, name | Coordination, Marketing, Website, Design & Video |
| Client | id, name, type (Doctor / Clinic / Hospital), speciality, account_owner_user_id, onboarded_on, renewal_date, active | Doctor type has a speciality; Clinic and Hospital don't |
| TaskTemplate | id (e.g. RAG-W1), title, team_id, default_assignee_ids, section, trigger_type, starts_when, repeat, weekday, day_of_month, time_start, time_end, input_from, input_needed, hand_off_to, done_when, priority, per_client (bool), is_time_block (bool), project_template_id, source, needs_confirmation, notes | One row per template in tab 5 |
| TemplateDependency | template_id, depends_on_template_id, kind (same-team / cross-team) | From the Depends On and Waiting On (Cross-Team) columns |
| TaskInstance | id, template_id, client_id, project_id, period_key (e.g. 2026-10-27, 2026-W44, 2026-10), assignee_id, status, due_at, started_at, completed_at, revision_count, approved_by, created_by (system / user) | What people actually work on |
| Project | id, project_template (New Website Build, New Client Onboarding), client_id, status, started_on | Groups instances created together |

Supporting tables: Comment (instance_id, user_id, text, file_url), ActivityLog (instance_id, user_id, action, old_value, new_value, at) and Notification (user_id, instance_id, channel, message, sent_at, read_at).

Every status change must be written to ActivityLog; reports and escalations depend on it.

## Automation rules

These ten rules are the heart of the system; everything else is screens around them.

- Daily scheduler (9:30 AM, Mon–Sat). Create today's instances for every Daily template, every Weekly template whose weekday is today, and every Monthly template whose day of month is today. Per-client templates create one instance per active client. Skip Sundays and a configurable holiday list.

- Lead time for monthly deadlines. Monthly tasks are created 3 working days before their due day (e.g. "Designs by 15th" appears on the 12th), so people see them coming.

- Dependency unlock. When an instance is marked Done, find every instance that depends on it. If all of its dependencies are now Done, move it from Locked or Waiting on Input to To Do and notify its assignee.

- Waiting on input. A Dependent task is created as Waiting on Input. The system also creates (or links to) the provider's task, e.g. Raghu's "Get service content" links to Shaheena's "Write website content". The provider is notified immediately and reminded every working day at 10 AM until they deliver.

- Project creation. "Onboard new client" (an admin or Shaheena) creates the New Client Onboarding project. Marking the onboarding task Done offers a "Start website build" button, which creates Raghu's 9-step chain and the linked tasks for Shaheena, Marketing and Design.

- Escalation. A task 1 working day overdue alerts the assignee's escalation contact (Shaheena). 2 working days overdue alerts both admins. High priority tasks escalate after 4 working hours instead of 1 day.

- Daily plan & approval (6:00 PM). Each person gets a "Plan for tomorrow" form pre-filled with their open tasks. Either admin approves or edits each plan; unapproved plans are flagged at 10 AM next day.

- Client edits & revision count. "Client sent changes" on an In Review task moves it back to To Do, increases revision_count and notifies the assignee. More than 2 rounds flags it to the admins.

- On-event tasks. A button (and later a webhook) for: new GMB query, negative review, website update request, shoot request, someone absent (creates a backup task for Shaheena).

- Weekly digest (Saturday 5 PM). Both admins receive completed vs overdue counts per person and per client, plus all tasks Waiting on Input for more than 2 days. Shown in-app on day one; email later.

## Rules that keep the app from breaking

Follow these exactly; most task systems collapse because tasks block forever, duplicate, or link to the wrong client.

1. Dependency scope (most important). A dependency only counts between instances in the same scope:

- Same project (website build, onboarding): match by project_id. Use this when both templates belong to the same project template (field project_template in tab 5). Across two projects, e.g. RAG-W1 (New Website Build) waiting on MKT-M19 (New Client Onboarding), match by client.

- Same client: a per-client task only waits on the dependency's instance for that same client.

- Same period: daily = same date, weekly = same week (Mon–Sat), monthly = same month.

A dependency is satisfied when the most recent instance of the dependency template in the same scope, created on or before the dependent task's due date, is Done. all mode needs every listed dependency satisfied; any mode needs one. Tasks with Repeat "On event", "On request", "As needed", "Per shoot", "Per post" or "Per piece" are not scheduled: whoever creates one links the exact provider task it waits on, so no matching is needed.

2. Nothing waits forever. If no instance of the dependency exists in scope, the dependent task is created as To Do with a "No input task found" flag, never Locked. Any task Waiting on Input for more than 3 working days appears on the Admin dashboard. Dependent templates with no Waiting On task (the input comes from a client or an admin, e.g. MKT-M19, DV-C1) are created as To Do; the assignee sets Waiting on Input manually and must name who they are waiting on.

3. No cycles. The import script checks the dependency graph and stops with a list of any cycle. The seed data in tab 5 has none.

4. Tasks with several assignees.

- Daily Schedule templates create one instance per listed person.

- Per-client tasks go to the client's account owner if that person is in the list.

- Otherwise the task is a team task: visible to everyone listed, and the first person to press Start becomes the assignee.

5. Daily Schedule time blocks. Templates in the section "Daily Schedule" (flag is_time_block in tab 5, 17 templates) show in My Day and can be ticked, but have no dependencies, are never Locked, never escalated and not counted as overdue. Exceptions: MKT-DS7, RAG-D7 and DV-D6 ("Plan for tomorrow & take approval") are required and escalate if missed.

6. Allowed status changes. Anything not in this table is rejected by the server, not just hidden in the UI.

| From | To | Who |
| --- | --- | --- |
| Locked | To Do | System only, when dependencies are satisfied |
| To Do | In Progress | Assignee |
| In Progress | In Review, Waiting on Input, Done | Assignee |
| Waiting on Input | To Do | System when input arrives; Shaheena or admins manually |
| In Review | Done | Shaheena or admins |
| In Review | To Do (client changes, revision +1) | Shaheena or admins |
| Done | To Do (reopen) | Admins only, with a reason |
| Any | Cancelled | Shaheena or admins |

7. No duplicates. Every scheduled instance has a unique key: template id + client id + period. Running the scheduler twice creates nothing new. If the scheduler missed days (server down), the next run catches up to 3 working days back, but skips past Daily Schedule time blocks.

8. Editing templates. Changes apply only to future instances. Deactivating a template stops new instances; open ones stay.

9. People leaving. Deactivating a user forces an admin to reassign their open tasks first and flags templates where they are the default assignee.

10. Time. Store all times in UTC; schedule and display in Asia/Kolkata. Working days are Mon–Sat, plus an admin-edited holiday list.

11. Protecting the existing app.

- Back up the database and test every migration on a copy of production data first.

- Only add tables and columns; never drop or rename existing ones.

- One setting, NEW_ENGINE_ENABLED, turns the new scheduler, unlocking and escalation off without a redeploy.

- The scheduler logs every run (tasks created, errors). One bad template must not stop the whole run.

12. Notification limits. At most one reminder per task per day, and reminders are grouped into one morning summary per person.

13. Database indexes. Unique index on (template id, client id, period key); indexes on (assignee, status, due date) and on dependency lookups.

## Screens

Nine screens, all mobile-friendly, since the team checks work on their phones. Reuse any screen the app already has and only add what is missing.

| Screen | Who | What it shows |
| --- | --- | --- |
| Public board | Anyone with the link, no login | Everyone's tasks today, read-only: grouped by person, with status, due time and overdue flag; filter by team and person |
| My Day | Everyone | Today's tasks in time-slot order, then overdue, then upcoming; one-tap status change |
| Waiting on Me | Everyone | Tasks where someone else is blocked on my input, oldest first, with who is waiting |
| I'm Waiting On | Everyone | My tasks blocked by others, with the provider and how many days |
| Task detail | Everyone | Description, Done When, dependencies (both ways), comments, files, history |
| Team board | Shaheena, Admins | Kanban by status, filter by team, person, client |
| Client view | Shaheena, Admins, Marketing | All open and recent tasks for one client, monthly deliverables checklist |
| Admin dashboard | Abhista, Raviteja | Overdue by person, blocked chains, plans awaiting approval, revision flags, weekly digest |
| Admin settings | Abhista, Raviteja | Users, teams, clients, task templates, project templates, holidays, public board link |

Adding or editing a template in Admin must not need a developer.

Public board rules, because it opens without a login and client names are visible:

- It lives at a long secret link (e.g. /board/8f3k…), not a guessable address. Admins can regenerate the link at any time, which turns the old one off.

- It is strictly read-only: no buttons, no comments, no status changes.

- It hides sensitive fields: payments, client phone numbers, logins, comments and attached files.

- It tells search engines not to index it.

- It refreshes every 60 seconds, so it can stay open on an office TV.

## Notifications

Start with in-app notifications; add WhatsApp after launch day, because Meta must verify the business account and approve message templates, which takes days and cannot fit in a one-day build.

| Event | Who is notified | Launch day → later |
| --- | --- | --- |
| Task unlocked / assigned | Assignee | In-app → WhatsApp |
| Input requested | Provider | In-app → WhatsApp |
| Daily input reminder (10 AM) | Provider of each Waiting on Input task | In-app → WhatsApp |
| Overdue 1 day | Shaheena | In-app → WhatsApp |
| Overdue 2 days / High priority 4 hours | Abhista and Raviteja | In-app → WhatsApp |
| Plan for tomorrow (6 PM) | Everyone | In-app |
| Plans awaiting approval | Abhista and Raviteja | In-app → WhatsApp |
| Revision rounds over 2 | Abhista and Raviteja | In-app |
| Weekly digest (Saturday 5 PM) | Abhista and Raviteja | In-app → email |

WhatsApp must use the official WhatsApp Business API through a provider (e.g. Interakt, Gupshup, Twilio), not an unofficial library, to avoid the number being banned. Messages must be batched: one morning summary per person, not one message per task.

## Build plan (one day) & acceptance criteria

All phases ship in one working day, which is only realistic because the app already exists and WhatsApp and email wait until after launch. Plan a second half-day for fixes once the team starts using it.

- 10:00–11:00 · Audit. Cursor compares the existing app with this document and lists what exists, what needs changing and what is missing. Developer and an admin agree the list. Back up the database.

- 11:00–1:00 · Data. Additive schema changes only (no data loss), import the seed data from tab 5, set Abhista and Raviteja as admins, set roles and escalation contacts.

- 2:00–4:00 · Engine. Scheduler, dependency unlock, waiting on input, escalation, revision count, project creation, daily plan approval.

- 4:00–6:00 · Screens. Public board, My Day, Waiting on Me, I'm Waiting On, Admin dashboard, plan approval, Client view. Reuse existing screens wherever possible.

- 6:00–7:30 · Test & deploy. Run the checklist below on a phone and a laptop, fix, deploy.

- Next day 9:30 AM · Watch the first run. Check that the scheduler created everyone's tasks, then share the public board link with the team.

After launch: WhatsApp notifications, weekly digest by email, webhooks for on-event tasks.

Launch day is done when:

- ☐ Existing data and users still work after the changes

- ☐ Importing the seed data from tab 5 creates all people, teams and templates with no errors, and running it twice creates no duplicates

- ☐ Abhista and Raviteja can log in as admins and see every team's tasks

- ☐ The public board link opens in a private browser window with no login, shows everyone's tasks, has no edit controls and no payment or phone details

- ☐ Regenerating the public link turns the old link off

- ☐ Running the scheduler for a Monday gives every person the right daily and Monday tasks in My Day

- ☐ Marking RAG-W5 Done unlocks SHA-AM1 for Shaheena; marking SHA-AM1 Done unlocks RAG-W6 for Raghu

- ☐ Shaheena sees "Write website content" in Waiting on Me when Raghu's step 2 is waiting

- ☐ A task set to overdue by 2 days alerts both admins

- ☐ Every status change appears in the task's history

- ☐ All screens work on a phone

If the audit shows the existing app is missing large basics (for example no dependency or recurring-task support at all), agree with the developer which screens move to day two rather than shipping everything half-done.

## Assumptions & open decisions

The seed data uses the assumptions below so the developer can start now; each is a single field to change later.

| Topic | Assumed in seed data | To confirm |
| --- | --- | --- |
| Client WhatsApp communication | Shaheena owns it; Marketing's duplicate task removed | Admins |
| Account Manager (domain confirmation, client changes on websites) | Shaheena | Admins |
| Assigning tasks to team | Shaheena; Marketing's duplicate removed | Admins |
| Video tracking | Design & Video team update the tracker; Shaheena monitors; Marketing's duplicate removed | Admins |
| GMB liners | Shaheena writes, Marketing posts | Admins |
| Animated videos | Bhavya and Chaithanya | Confirmed |
| Service images for websites | Design team provides; Raghu's step 3 waits on them | Raghu |
| Internal website audit | Admins | Admins |
| Frequencies marked "(confirm)" | Weekly, except payment checks (daily) | Each team |
| Suggested tasks (marked Suggested) | Included and active | Admins can deactivate any in Admin |
| Working days & start time | Mon–Sat, 10:00 AM to 6:30 PM | Admins |

Removed duplicates are listed under merged_and_removed in tab 5.

Decided since the first draft: the app already exists, Abhista and Raviteja are the two admins, everyone's tasks are visible without login through the public board link, and everything except WhatsApp and email ships in one day.