## Task Templates
Task ID | Task | Team | Assignee(s) | Section | Trigger Type | Starts When | Repeat | Time / Day | Depends On (Same Team) | Waiting On (Cross-Team) | Input From | Input Needed | Hand Off To | Done When | Priority | Per Client | Needs Confirmation | Source | Notes
SHA-S1 | Client communication on WhatsApp groups | Coordination | Shaheena | Coordination | Auto (Scheduled) | Several times daily | Daily | 10 AM / 2 PM / 5 PM |  |  | Client | Client messages & requests | Relevant team member | All client messages answered same day | High | No | No | Shaheena's board | Single owner – Marketing duplicate removed
SHA-S2 | Assign tasks to team | Coordination | Shaheena | Coordination | Self-Trigger | New request from client or Admins (Abhista, Raviteja) | Daily | 10:00–11:00 AM | SHA-S1 |  |  |  | Assigned person | Every request has owner & due date | High | No | No | Shaheena's board | Single owner – Marketing duplicate removed
SHA-S7 | Coordinate with team & escalate delayed work | Coordination | Shaheena | Coordination | Auto (Scheduled) | Every working day | Daily | 4:00 PM | SHA-S2 |  |  |  | Admins (Abhista, Raviteja) | Overdue tasks escalated | High | No | No | Shaheena's board | Suggest rule: escalate if overdue by 1 day
SHA-S5 | Track videos | Coordination | Shaheena | Coordination | Auto (Scheduled) | Every working day | Daily |  |  |  | Design & Video Team | Video status |  | Video tracker updated | Medium | No | No | Shaheena's board | Single owner – Marketing duplicate removed
SHA-S6 | Check client profiles if needed | Coordination | Shaheena | Coordination | On Event | Request or issue on a profile | On event | [6 empty] | Profile checked & issue logged | Medium | No | No | Shaheena's board
SHA-S3 | Write website content (service pages, doctor profile) | Coordination | Shaheena | Content Writing | Dependent | New client onboarded | Per new website |  |  | MKT-M19 | Marketing (Gouthami & Ayesha) + Client | Client details (M19), doctor's resume, services list | Raghu (Developer) | Content approved & sent to Raghu (W2) | High | No | No | Shaheena's board
SHA-S4 | Write social media content (captions & post copy) | Coordination | Shaheena | Content Writing | Dependent | Monthly plan & client inputs ready | Monthly | By 10th |  | MKT-X2 | Marketing (Gouthami & Ayesha) | Client's offers/events for next month (X2) | Design & Video Team + Marketing (Gouthami & Ayesha) | Next month's copy with Design team | High | Yes | No | Shaheena's board | Needed so designs are ready by 15th
SHA-S8 | New ideas & creative concepts | Coordination | Shaheena | Content Writing | Auto (Scheduled) | Every week | Weekly | [5 empty] | Marketing (Gouthami & Ayesha) + Design & Video Team | Ideas shared in team review | Medium | No | No | Shaheena's board
SHA-S9 | Backup for video editing, poster design & social media work | Coordination | Shaheena | Backup (Joker) | Dependent | Someone absent or overloaded | On event |  |  |  | Admins (Abhista, Raviteja) | Task handed over |  | Backup task completed | Medium | No | No | Shaheena's board | Admins (Abhista, Raviteja) assigns; log so it's not counted against her main work
SHA-C1 | Write blogs for client websites | Coordination | Shaheena | Content Writing | Auto (Scheduled) | Every week | Weekly | [5 empty] | Raghu (Developer) | Blog sent to Raghu (his W9) | Medium | Yes | Yes | Added – other boards | Frequency assumed weekly
SHA-C2 | Write off-page SEO articles | Coordination | Shaheena | Content Writing | Auto (Scheduled) | Every week | Weekly | [5 empty] | Raghu (Developer) | Article sent to Raghu (his S2) | Medium | No | Yes | Added – other boards | Frequency assumed weekly
SHA-C3 | Write LinkedIn articles | Coordination | Shaheena | Content Writing | Auto (Scheduled) | Every week | Weekly | [5 empty] | Marketing (Gouthami & Ayesha) | Article sent to Marketing (their M7) | Medium | No | Yes | Added – other boards | Frequency assumed weekly
SHA-C4 | Write GMB liners | Coordination | Shaheena | Content Writing | Auto (Scheduled) | Every month | Monthly | By 28th |  |  |  |  | Marketing (Gouthami & Ayesha) | Liners ready before Marketing's 1st deadline | Medium | Yes | No | Added – other boards | Shaheena writes, Marketing posts (MKT-M10)
SHA-C5 | Write case studies from client pictures | Coordination | Shaheena | Content Writing | Dependent | Marketing collects case study pics (Thursday) | Weekly | Friday |  | MKT-A3 | Marketing (Gouthami & Ayesha) | Case study pictures & details | Marketing (Gouthami & Ayesha) + Raghu (Developer) | Case study written | Medium | No | No | Added – other boards
SHA-C6 | Content for website updates | Coordination | Shaheena | Content Writing | Dependent | Update request received | On event |  |  |  | Marketing (Gouthami & Ayesha) / Client | Update details | Raghu (Developer) | Content sent to Raghu (his M1) | Medium | No | No | Added – other boards
SHA-X1 | Write video scripts for shoots | Coordination | Shaheena | Content Writing | Dependent | Shoot scheduled by Marketing (M16) | Per shoot | 2 days before shoot |  | MKT-M16 | Marketing (Gouthami & Ayesha) | Shoot date & topic | Design & Video Team | Script approved | High | No | No | Suggested | Shoots go smoother with a ready script
SHA-X2 | Get client approval on content before handing over | Coordination | Shaheena | Content Writing | Dependent | Content draft ready | Per piece |  | SHA-S3, SHA-S4 |  | Client | Approval | Raghu (Developer) / Design & Video Team | Approved content handed over | High | No | No | Suggested | Avoids rework after design/development
SHA-X3 | Doctor review of medical claims in content | Coordination | Shaheena | Content Writing | Dependent | Content has treatment or health claims | Per piece |  |  |  | Client | Doctor's sign-off |  | No unverified health claims | High | No | No | Suggested
SHA-X4 | SEO keyword check for website content & blogs | Coordination | Shaheena | Content Writing | Self-Trigger | Before sending content | Per piece | [6 empty] | Target keywords included | Medium | No | No | Suggested | Use Marketing's keyword ranking list (M11)
SHA-X5 | Proofread all content | Coordination | Shaheena | Content Writing | Self-Trigger | Before handover | Per piece | [6 empty] | No spelling/grammar errors | Medium | No | No | Suggested
SHA-X6 | Maintain content library per client (tone, services, past posts) | Coordination | Shaheena | Content Writing | Self-Trigger | After each delivery | Ongoing | [6 empty] | Library up to date | Medium | No | No | Suggested
SHA-X7 | Reels / content trend research | Coordination | Shaheena | Content Writing | Auto (Scheduled) | Every week | Weekly | [5 empty] | Marketing (Gouthami & Ayesha) + Design & Video Team | Trends shared with S8 ideas | Medium | No | No | Suggested
SHA-X8 | End-of-day status update to Admins (Abhista, Raviteja) | Coordination | Shaheena | Coordination | Auto (Scheduled) | Every working day | Daily | 6:00 PM | SHA-S7 |  |  |  | Admins (Abhista, Raviteja) | Pending & escalated items shared | High | No | No | Suggested
SHA-AM1 | Send website preview to client & collect changes | Coordination | Shaheena | Website Projects | Dependent | Raghu's internal audit passed (RAG-W5) | Per new website |  |  | RAG-W5 | Raghu (Developer) + Client | Preview link; client's changes | Raghu | Client's change list or approval sent to Raghu | High | No | Yes | Added – master | Shaheena acts as Account Manager (assumed)
SHA-AM2 | Get domain confirmation from client | Coordination | Shaheena | Website Projects | Dependent | Client approves website (RAG-W6) | Per new website |  |  | RAG-W6 | Raghu (Developer) + Client | Domain name & access | Raghu | Domain confirmed & access shared with Raghu | High | No | Yes | Added – master | Shaheena acts as Account Manager (assumed)
MKT-DS1 | Check Marketing requests & reply to ads / GMB / social queries | Marketing | Gouthami, Ayesha | Daily Schedule | Auto (Scheduled) | 10:00 every working day | Daily (Mon–Sat) | 10:00–11:00 AM | [5 empty] | Requests assigned to the right person | High | No | No | Main board
MKT-DS2 | Send reminders & check message alerts | Marketing | Gouthami, Ayesha | Daily Schedule | Auto (Scheduled) | 11:00 every working day | Daily (Mon–Sat) | 11:00–11:30 AM | [5 empty] | Reminders sent | High | No | No | Main board
MKT-DS3 | Review responses | Marketing | Gouthami, Ayesha | Daily Schedule | Auto (Scheduled) | 11:30 AM every working day | Daily (Mon–Sat) | 11:30 AM–12:00 PM | [5 empty] | Responses reviewed | High | No | No | Main board
MKT-DS4 | Follow up on team's work, get approval & update client | Marketing | Gouthami, Ayesha | Daily Schedule | Auto (Scheduled) | 2:00 every working day | Daily (Mon–Sat) | 2:00–2:30 PM | [5 empty] | Clients updated | High | No | No | Main board
MKT-DS5 | Follow up on given creatives & get changes done | Marketing | Gouthami, Ayesha | Daily Schedule | Auto (Scheduled) | 2:30 every working day | Daily (Mon–Sat) | 2:30–4:00 PM | [5 empty] | Changes closed | High | No | No | Main board
MKT-DS6 | Coordinate with team for work | Marketing | Gouthami, Ayesha | Daily Schedule | Auto (Scheduled) | 4:00 every working day | Daily (Mon–Sat) | 4:00–4:30 PM | [5 empty] | Team aligned for tomorrow | High | No | No | Main board
MKT-DS7 | Plan for tomorrow & take approval | Marketing | Gouthami, Ayesha | Daily Schedule | Dependent | 6:00 every working day | Daily (Mon–Sat) | 6:00–6:30 PM |  |  | Admins (Abhista, Raviteja) | Approval of plan |  | Plan approved | High | No | No | Main board
MKT-M19 | Take onboarding details from new client | Marketing | Gouthami, Ayesha | Client Communication | Dependent | Admins (Abhista, Raviteja) confirms new client signed | Per new client |  |  |  | Admins (Abhista, Raviteja) / Client | Signed client, business details, photos, logins (GMB, socials) | Raghu (Developer), Shaheena (Content Writer), Design & Video Team | Onboarding sheet complete & shared | High | No | No | Marketing board | This is Raghu's W1 input
MKT-M13 | Review reminders to clients | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every Monday | Weekly | Monday | [5 empty] | Reminder sent to all clients | Medium | Yes | No | Marketing board
MKT-A1 | Ask clients for photos | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every Tuesday | Weekly | Tuesday |  |  |  |  | Design & Video Team | Photos received & shared with Design team | Medium | Yes | No | Added – main board
MKT-A2 | Performance review calls with clients | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every Wednesday | Weekly | Wednesday | MKT-M20 |  |  |  |  | Calls done | Medium | Yes | No | Added – main board
MKT-A3 | Ask clients for case study pictures | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every Thursday | Weekly | Thursday |  |  |  |  | Shaheena (Content Writer) | Pictures received | Medium | Yes | No | Added – main board
MKT-A4 | Client communication reminders | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every Saturday | Weekly | Saturday | [5 empty] | Pending items reminded | Medium | Yes | No | Added – main board
MKT-M3 | Upload creatives & videos with alt text | Marketing | Gouthami, Ayesha | Social Media & Content | Dependent | Approved creative/video received | Per post |  | MKT-M14 | DV-V3 ¦ DV-P1 | Design & Video Team + Client | Final creatives/videos (Design team) + client approval |  | Posted with alt text | High | No | No | Marketing board
MKT-M4 | Track social media accounts | Marketing | Gouthami, Ayesha | Social Media & Content | Auto (Scheduled) | Every working day | Daily | [6 empty] | Growth & engagement logged | Medium | No | No | Marketing board
MKT-M7 | Post LinkedIn articles | Marketing | Gouthami, Ayesha | Social Media & Content | Dependent | Shaheena delivers article | Weekly |  |  | SHA-C3 | Shaheena (Content Writer) | Article content |  | Article published | Medium | No | Yes | Marketing board | Frequency assumed weekly
MKT-M14 | Schedule monthly posts & videos (after client confirmation) | Marketing | Gouthami, Ayesha | Social Media & Content | Dependent | Designs ready (15th) & client confirms (20th) | Monthly | By 25th |  | DV-P1 | Design & Video Team + Client | Next month's designs; client approval |  | All next-month posts scheduled | High | Yes | Yes | Marketing board
MKT-M16 | Schedule shoots | Marketing | Gouthami, Ayesha | Social Media & Content | Dependent | Client confirms date | As needed |  |  |  | Client | Shoot date & availability | Design & Video Team | Shoot booked & video team informed | Medium | No | No | Marketing board
MKT-M6 | Send updated links to developer for website | Marketing | Gouthami, Ayesha | Social Media & Content | Self-Trigger | After M3 / new content goes live | As needed |  | MKT-M3 |  |  |  | Raghu (Developer) | Raghu has links | Medium | No | No | Marketing board | Feeds Raghu's M1 (website updates)
MKT-M8 | GMB, Facebook, YouTube, Instagram & LinkedIn profile optimisation | Marketing | Gouthami, Ayesha | GMB | Self-Trigger | Weekly / when ranking drops | Weekly |  | MKT-M11 |  |  |  |  | Profiles optimised | Medium | No | Yes | Marketing board | Frequency assumed weekly
MKT-M10 | Prepare GMB liners (post captions) | Marketing | Gouthami, Ayesha | GMB | Dependent | Shaheena delivers liners | Monthly | By 1st |  | SHA-C4 | Shaheena | Liners text if Shaheena writes them |  | Liners schedule complete | High | Yes | No | Marketing board | Shaheena writes (SHA-C4), Marketing posts
MKT-M11 | Check profile ranking for keywords | Marketing | Gouthami, Ayesha | GMB | Auto (Scheduled) | Every week | Weekly | [6 empty] | Rankings logged, low performers flagged | Medium | Yes | No | Marketing board
MKT-M15 | Monitor GMB | Marketing | Gouthami, Ayesha | GMB | Auto (Scheduled) | Every working day | Daily | [6 empty] | All GMBs checked | High | Yes | No | Marketing board
MKT-M18 | Reply to GMB queries | Marketing | Gouthami, Ayesha | GMB | On Event | New query on GMB | On event |  | MKT-M15 |  |  |  |  | Replied same day | High | No | No | Marketing board
MKT-M17 | Escalate negative reviews | Marketing | Gouthami, Ayesha | GMB | On Event | Negative review found | On event |  | MKT-M15 |  |  |  | Admins (Abhista, Raviteja) / Client | Escalated within the day | High | No | No | Marketing board
MKT-M5 | Run Meta Ads & Google Ads | Marketing | Gouthami, Ayesha | Ads | Dependent | Ad creatives & budget approved | Weekly (Friday review) | Friday |  | DV-C1 | Design & Video Team + Client | Ad creatives; client budget approval |  | Campaigns live & monitored | High | No | No | Marketing board
MKT-M20 | Track performance & send to client | Marketing | Gouthami, Ayesha | Reports | Auto (Scheduled) | Every week | Weekly | Before Wednesday calls |  | RAG-M4, RAG-A4 | Raghu (Developer) | Website & appointment reports | Client | Report sent to client | High | Yes | No | Marketing board
MKT-M12 | Monthly reports of everything | Marketing | Gouthami, Ayesha | Reports | Auto (Scheduled) | Monthly | Monthly | By 8th | MKT-M20 | RAG-M4, RAG-A4 | Raghu (Developer) + Design & Video Team | Website, ads, social & GMB data | Client | All client reports sent | High | Yes | No | Marketing board | Main board: reports due on 8th
MKT-X1 | Send monthly content brief to Design & Video team | Marketing | Gouthami, Ayesha | Social Media & Content | Self-Trigger | After client strategy input | Monthly | By 10th | MKT-X2 |  |  |  | Design & Video Team | Brief shared so designs are ready by 15th | High | No | No | Suggested | Designers can't start next month without this
MKT-X2 | Monthly content planning check-in with client (offers, events, new services) | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every month | Monthly | By 5th | [5 empty] | Client inputs noted | Medium | Yes | No | Suggested
MKT-X3 | Chase pending post approvals | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | 3 days after posts sent (20th) | Monthly | 23rd | MKT-M14 |  | Client | Approval |  | All clients approved | Medium | Yes | No | Suggested
MKT-X4 | Follow up on pending payments | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every week | Weekly | [5 empty] | Admins (Abhista, Raviteja) | Pending list updated & shared with Admins (Abhista, Raviteja) | High | No | No | Suggested | Was on your weekly goals
MKT-X5 | Contract renewal reminders | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | 30 days before renewal date | Monthly check | [5 empty] | Admins (Abhista, Raviteja) | Renewals flagged to Admins (Abhista, Raviteja) | Medium | No | No | Suggested
MKT-X6 | Client satisfaction check | Marketing | Gouthami, Ayesha | Client Communication | Auto (Scheduled) | Every quarter | Quarterly | [6 empty] | Feedback logged & issues raised | Medium | Yes | No | Suggested
MKT-X7 | Health awareness days & festival calendar for posts | Marketing | Gouthami, Ayesha | Social Media & Content | Auto (Scheduled) | Every month | Monthly | By 5th |  |  |  |  | Design & Video Team | Key days added to next month's plan | Medium | No | No | Suggested | e.g. World Heart Day, Diabetes Day – useful for clinic clients
MKT-X8 | Reply to comments & DMs on all client pages | Marketing | Gouthami, Ayesha | Social Media & Content | Auto (Scheduled) | Every working day | Daily | [6 empty] | No comment/DM left unanswered | High | No | No | Suggested
MKT-X9 | Medical content compliance check before posting | Marketing | Gouthami, Ayesha | Social Media & Content | Self-Trigger | Before every upload | Per post | [6 empty] | No banned claims, patient photos have consent | High | No | No | Suggested | Ad platforms and medical guidelines restrict health claims and testimonials
MKT-X10 | Store approved creatives & logins in shared drive | Marketing | Gouthami, Ayesha | Social Media & Content | Self-Trigger | After upload / onboarding | Per post |  | MKT-M3 |  |  |  |  | Files & access saved | Medium | No | No | Suggested
MKT-X11 | Post weekly GMB updates & photos | Marketing | Gouthami, Ayesha | GMB | Auto (Scheduled) | Every week | Weekly |  | MKT-M10 |  |  |  |  | Each GMB has a fresh post | Medium | Yes | No | Suggested
MKT-X12 | Reply to all Google reviews (positive & negative) | Marketing | Gouthami, Ayesha | GMB | Auto (Scheduled) | Every working day | Daily | 11:30 AM–12:00 PM | MKT-M15 |  |  |  |  | All new reviews answered | High | No | No | Suggested
MKT-X13 | Update GMB hours, holidays & services | Marketing | Gouthami, Ayesha | GMB | On Event | Client informs change / holiday | On event |  |  |  | Client | New timings or services |  | GMB info correct | Medium | No | No | Suggested
MKT-X14 | Daily ad spend & performance check | Marketing | Gouthami, Ayesha | Ads | Auto (Scheduled) | Every working day | Daily |  | MKT-M5 |  |  |  |  | Spend on track, poor ads paused | High | No | No | Suggested
MKT-X15 | Send ad leads to client / clinic | Marketing | Gouthami, Ayesha | Ads | Auto (Scheduled) | Every working day | Daily |  | MKT-M5 |  |  |  | Client | All leads forwarded same day | High | Yes | No | Suggested | Leads go cold fast for clinics
MKT-X16 | Monthly ad budget approval & creative refresh | Marketing | Gouthami, Ayesha | Ads | Dependent | Start of month | Monthly | By 1st |  |  | Client + Design & Video Team | Budget approval; new ad creatives |  | Budget & creatives approved | Medium | Yes | No | Suggested
MKT-X17 | Track follower growth vs 20% target | Marketing | Gouthami, Ayesha | Reports | Auto (Scheduled) | Every week | Weekly |  | MKT-M4 |  |  |  |  | Growth % logged per client | Medium | Yes | No | Suggested
MKT-X18 | Flag low-performing clients with action plan | Marketing | Gouthami, Ayesha | Reports | Self-Trigger | After weekly ranking & growth check | Weekly |  | MKT-M11 |  |  |  | Admins (Abhista, Raviteja) | Action plan shared with Admins (Abhista, Raviteja) | Medium | No | No | Suggested
MKT-X19 | Competitor tracking | Marketing | Gouthami, Ayesha | Reports | Auto (Scheduled) | Every month | Monthly | [6 empty] | Competitor notes added to report | Medium | No | No | Suggested
MKT-X20 | Weekly internal team review | Marketing | Gouthami, Ayesha | Reports | Auto (Scheduled) | Every Saturday | Weekly | Saturday |  |  |  |  | Admins (Abhista, Raviteja) | Pending work reviewed with all teams | Medium | No | No | Suggested
RAG-D1 | Note down new tasks or requests | Website | Raghu | Daily Schedule | Auto (Scheduled) | 10:00 AM every working day | Daily (Mon–Sat) | 10:00–10:30 AM |  | SHA-S2 | Shaheena (Coordinator) | New client requests for website |  | All requests logged as tasks | High | No | No | Main board
RAG-D2 | Complete requests | Website | Raghu | Daily Schedule | Auto (Scheduled) | 10:30 AM every working day | Daily (Mon–Sat) | 10:30 AM–12:00 PM | RAG-D1 |  |  |  |  | Today's requests closed or updated | High | No | No | Main board
RAG-D3 | Google Reserve – update appointment booking | Website | Raghu | Daily Schedule | Auto (Scheduled) | 12:00 PM every working day | Daily (Mon–Sat) | 12:00–1:00 PM | [5 empty] | Bookings synced on Google | High | No | No | Main board
RAG-D4 | Regular works (builds / maintenance / SEO) | Website | Raghu | Daily Schedule | Auto (Scheduled) | 2:00 PM every working day | Daily (Mon–Sat) | 2:00–4:00 PM | [6 empty] | Medium | No | No | Main board
RAG-D5 | Recheck pending edits | Website | Raghu | Daily Schedule | Auto (Scheduled) | 4:00 PM every working day | Daily (Mon–Sat) | 4:00–5:00 PM | [5 empty] | No edits left pending | High | No | No | Main board
RAG-D6 | Regular works (builds / maintenance / SEO) | Website | Raghu | Daily Schedule | Auto (Scheduled) | 5:00 PM every working day | Daily (Mon–Sat) | 5:00–6:00 PM | [6 empty] | Medium | No | No | Main board
RAG-D7 | Plan for tomorrow & take approval | Website | Raghu | Daily Schedule | Dependent | 6:00 PM every working day | Daily (Mon–Sat) | 6:00–6:30 PM |  |  | Admins (Abhista, Raviteja) | Approval of tomorrow's plan |  | Plan approved | High | No | No | Main board
RAG-W1 | Collect website details – name, client type, location, phone, photos, social links, GMB | Website | Raghu | New Website Build | Dependent | Shaheena (Coordinator) onboards new client & shares details | Per new website |  |  | MKT-M19 | Shaheena (Coordinator) | Client details, photos, social links, GMB access |  | All details received | High | No | No | Website board | Client type: Doctor (speciality) / Clinic / Hospital
RAG-W2 | Get service content & doctor's resume | Website | Raghu | New Website Build | Dependent | Shaheena delivers content | Per new website |  | RAG-W1 | SHA-S3 | Shaheena (Content Writer) + Shaheena (Coordinator) | Service content (Shaheena); doctor's resume & special requirements (Shaheena (Coordinator) from client) |  | Content complete | High | No | No | Website board
RAG-W3 | Website layout & service images | Website | Raghu | New Website Build | Dependent | Design team delivers service images | Per new website |  | RAG-W2 | DV-C3 | Design & Video Team | Service images |  | Layout ready | High | No | No | Website board
RAG-W4 | Development – design, code, meta titles, schema, disclaimer, privacy policy, AEO/GEO/SEO, on-page SEO | Website | Raghu | New Website Build | Self-Trigger | W3 done | Per new website |  | RAG-W3 |  |  |  |  | Site built on preview link | High | No | No | Website board
RAG-W5 | Internal audit of preview link → edits → updated link | Website | Raghu | New Website Build | Dependent | Preview link shared for audit | Per new website |  | RAG-W4 |  | Admins (Abhista, Raviteja) | Audit feedback on preview |  | Internal audit passed | High | No | Yes | Website board | Confirm who does the internal audit
RAG-W6 | Client review → changes → update | Website | Raghu | New Website Build | Dependent | Shaheena (Coordinator) sends preview to client | Per new website |  | RAG-W5 | SHA-AM1 | Shaheena (Coordinator) | Client's change list & approval | Shaheena (Coordinator) | Client approval received | High | No | No | Website board
RAG-W7 | Domain confirmation → make website live | Website | Raghu | New Website Build | Dependent | Shaheena (Coordinator) confirms domain with client | Per new website |  | RAG-W6 | SHA-AM2 | Shaheena (Coordinator) | Domain name & access confirmed by client | Shaheena (Coordinator) | Website live on domain | High | No | Yes | Website board | Hand off: inform Shaheena (Coordinator) site is live
RAG-W8 | Google indexing, Search Console & performance analysis | Website | Raghu | New Website Build | Self-Trigger | W7 done | Per new website |  | RAG-W7 |  |  |  |  | Indexed & Search Console verified | High | No | No | Website board
RAG-W9 | Publish blogs on a regular basis | Website | Raghu | New Website Build | Dependent | Shaheena delivers blog | Ongoing |  | RAG-W8 | SHA-C1 | Shaheena (Content Writer) | Blog content |  | Blog published | Medium | No | No | Website board
RAG-M1 | Update videos, photos & blogs on website | Website | Raghu | Website Maintenance | Dependent | Update received from client or internal team | On request |  |  | SHA-C6 ¦ DV-C4 ¦ MKT-M6 | Shaheena (Coordinator) / Shaheena (Content Writer) / Design & Video Team | Files or content to update |  | Update live on site | Medium | No | No | Website board | Client updates come via Shaheena (Coordinator)
RAG-M2 | Website monitoring – 3 clients | Website | Raghu | Website Maintenance | Auto (Scheduled) | Every working day | Daily | [6 empty] | All 3 sites checked, issues logged | High | Yes | No | Website board
RAG-M3 | Check performance & make changes if needed | Website | Raghu | Website Maintenance | Self-Trigger | Issue found in M2 or weekly check | Weekly |  | RAG-M2 |  |  |  |  | Changes done or none needed | Medium | No | Yes | Website board | Frequency assumed weekly
RAG-M4 | Website performance report | Website | Raghu | Website Maintenance | Auto (Scheduled) | Every week | Weekly |  | RAG-M3 |  |  |  | Shaheena (Coordinator) | Report shared with Account Manager | High | Yes | No | Website board
RAG-A2 | Check online payments | Website | Raghu | Appointment Booking | Auto (Scheduled) | Every working day | Daily | [6 empty] | Payments matched with bookings | High | No | Yes | Website board | Frequency assumed daily
RAG-A3 | Improvements to booking system | Website | Raghu | Appointment Booking | Dependent | Issue or request raised | On request |  |  |  | Shaheena (Coordinator) / Client | Problem or improvement request |  | Change deployed | Medium | No | No | Website board
RAG-A4 | Appointment report to client & doctor | Website | Raghu | Appointment Booking | Auto (Scheduled) | Every week | Weekly |  | RAG-A2 |  |  |  | Shaheena (Coordinator) | Report sent | Medium | Yes | Yes | Website board | Frequency assumed weekly
RAG-S1 | Off-page SEO – link building | Website | Raghu | Off-Page SEO | Self-Trigger | Every week | Weekly |  | RAG-W8 |  |  |  |  | Links logged | Medium | No | Yes | Website board | Frequency assumed weekly
RAG-S2 | Off-page SEO – publish blogs & articles on external sites | Website | Raghu | Off-Page SEO | Dependent | Shaheena delivers article | Weekly |  |  | SHA-C2 | Shaheena (Content Writer) | Articles / blog content |  | Articles published | Medium | No | Yes | Website board | Frequency assumed weekly
DV-D1 | Task revisions & additional tasks | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Daily Schedule | Auto (Scheduled) | 10:00 every working day | Daily (Mon–Sat) | 10:00–10:30 AM | [5 empty] | Revisions from yesterday closed | High | No | No | Main board
DV-D2 | Emergency work, rework or edits | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Daily Schedule | Auto (Scheduled) | 10:30 every working day | Daily (Mon–Sat) | 10:30–11:00 AM | [5 empty] | Urgent items done | High | No | No | Main board
DV-D3 | New / allotted tasks | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Daily Schedule | Auto (Scheduled) | 11:00 AM every working day | Daily (Mon–Sat) | 11:00 AM–1:00 PM | [5 empty] | Progress updated in tracker | High | No | No | Main board
DV-D4 | Continue new / allotted tasks | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Daily Schedule | Auto (Scheduled) | 2:00 every working day | Daily (Mon–Sat) | 2:00–4:00 PM | [5 empty] | Progress updated in tracker | High | No | No | Main board
DV-D5 | Works & revisions | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Daily Schedule | Auto (Scheduled) | 4:00 every working day | Daily (Mon–Sat) | 4:00–6:00 PM | [5 empty] | Revisions sent | High | No | No | Main board
DV-D6 | Plan for tomorrow & take approval | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Daily Schedule | Dependent | 6:00 every working day | Daily (Mon–Sat) | 6:00–6:30 PM |  |  | Admins (Abhista, Raviteja) | Approval of plan |  | Plan approved | High | No | No | Main board
DV-V1 | Outdoor video shoot | Design & Video | Dileep | Video | Dependent | Shoot scheduled by Marketing | Per shoot |  |  | MKT-M16, SHA-X1 | Marketing (Gouthami & Ayesha) + Shaheena | Shoot date & location (Marketing); script (Shaheena) |  | Footage shot & backed up | High | No | No | Design board
DV-V2 | In-house video shoot | Design & Video | Dileep | Video | Dependent | Shoot scheduled by Marketing | Per shoot |  |  | MKT-M16, SHA-X1 | Marketing (Gouthami & Ayesha) + Shaheena | Shoot date (Marketing); script (Shaheena) |  | Footage shot & backed up | High | No | No | Design board
DV-V3 | Video edit & thumbnail | Design & Video | Dileep, Rohit | Video | Self-Trigger | Footage ready after shoot | Per video |  | DV-V1 ¦ DV-V2 |  |  |  | Marketing (Gouthami & Ayesha) | Edited video & thumbnail sent for approval | High | No | Yes | Design board | Board shows Dileep & Rohit – confirm split
DV-P1 | Poster design | Design & Video | Rohit, Bhavya, Chaithanya | Poster & Animation | Dependent | Content brief & captions received | Monthly + on request | By 15th |  | MKT-X1, SHA-S4 | Marketing (Gouthami & Ayesha) + Shaheena | Monthly brief (Marketing, by 10th); captions (Shaheena) | Marketing (Gouthami & Ayesha) | Designs ready for client | High | Yes | No | Design board
DV-P2 | Animated videos | Design & Video | Bhavya, Chaithanya | Poster & Animation | Dependent | Brief & copy received | On request |  |  |  | Marketing (Gouthami & Ayesha) + Shaheena | Brief & script/copy | Marketing (Gouthami & Ayesha) | Animation sent for approval | Medium | No | Yes | Design board | Assumed – confirm Bhavya
DV-E1 | Make client edits & resubmit | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Client Edits | Dependent | Client sends changes | On event |  | DV-V3, DV-P1, DV-P2 |  | Shaheena / Marketing (Gouthami & Ayesha) | Client's change list | Marketing (Gouthami & Ayesha) | Revised file submitted | High | No | No | Design board | Changes come via coordinator, not directly from client
DV-C1 | Ad creatives for Meta & Google Ads | Design & Video | Chaithanya | Poster & Animation | Dependent | Ad request from Marketing | Monthly + on request | By 1st |  |  | Marketing (Gouthami & Ayesha) | Offer, budget, ad format | Marketing (Gouthami & Ayesha) | Ad creatives approved | Medium | No | No | Added – other boards | Main board had 'Ad post → Chaitanya'
DV-C2 | GMB post creatives & photos | Design & Video | Rohit, Bhavya | Poster & Animation | Dependent | GMB liners ready | Weekly |  |  | SHA-C4 | Marketing (Gouthami & Ayesha) / Shaheena | GMB liners | Marketing (Gouthami & Ayesha) | Creatives sent for GMB posts | Medium | Yes | No | Added – other boards
DV-C3 | Service images for new websites | Design & Video | Rohit, Bhavya | Poster & Animation | Dependent | Raghu requests images | Per new website |  |  |  | Raghu | Image list & sizes | Raghu | Images sent to Raghu | Medium | No | No | Added – other boards | If Raghu does these himself, delete
DV-C4 | Videos & photos for website updates | Design & Video | Dileep | Video | Dependent | Raghu or Marketing requests | On event |  |  |  | Raghu / Marketing (Gouthami & Ayesha) | What's needed | Raghu | Files sent to Raghu | Medium | No | No | Added – other boards
DV-C5 | Update video tracker | Design & Video | Dileep, Rohit | Video | Auto (Scheduled) | Every working day | Daily (Mon–Sat) | 6:00 PM | [5 empty] | Tracker shows latest status | High | No | No | Added – other boards | Marketing & Shaheena track videos from this
DV-C6 | Edit client photos received on Tuesdays | Design & Video | Rohit, Bhavya | Poster & Animation | Dependent | Marketing shares client photos | Weekly |  |  | MKT-A1 | Marketing (Gouthami & Ayesha) | Client photos | Marketing (Gouthami & Ayesha) | Photos edited & ready to use | Medium | No | No | Added – other boards
DV-X1 | Patient consent forms before filming | Design & Video | Dileep | Video | Dependent | Before every shoot with patients | Per shoot |  |  |  | Client / Marketing (Gouthami & Ayesha) | Signed consent |  | Consent on file | High | No | No | Suggested | Medical videos showing patients need written consent
DV-X2 | Equipment check & shot list day before shoot | Design & Video | Dileep | Video | Auto (Scheduled) | 1 day before each shoot | Per shoot | Day before | DV-V1 ¦ DV-V2 |  | Shaheena | Script |  | Batteries, cards, lights ready; shot list made | Medium | No | No | Suggested
DV-X3 | Back up raw footage & files to shared drive | Design & Video | Dileep | Video | Self-Trigger | Same day as shoot | Per shoot |  | DV-V1 ¦ DV-V2 |  |  |  |  | Footage in drive with client name & date | High | No | No | Suggested
DV-X4 | Brand kit per client (logo, colours, fonts, templates) | Design & Video | Rohit, Bhavya, Chaithanya | Poster & Animation | Self-Trigger | New client onboarded | Per new client |  |  |  | Marketing (Gouthami & Ayesha) | Logo & brand details |  | Brand kit in shared drive | Medium | No | No | Suggested
DV-X5 | Internal quality check before sending to client | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Client Edits | Self-Trigger | Before every submission | Per piece |  | DV-V3, DV-P1, DV-P2 |  |  |  |  | Checked for spelling, logo, phone no., sizes | High | No | No | Suggested
DV-X6 | Export in every platform size (Reels 9:16, YouTube 16:9, posts 1:1/4:5) | Design & Video | Dileep, Rohit | Video | Self-Trigger | After approval | Per video |  | DV-V3 |  |  |  | Marketing (Gouthami & Ayesha) | All sizes delivered | Medium | No | No | Suggested
DV-X7 | Use only royalty-free / licensed music | Design & Video | Dileep, Rohit, Chaithanya | Video | Self-Trigger | During edit | Per video | [6 empty] | Music source noted | Medium | No | No | Suggested | Avoids copyright strikes on client pages
DV-X8 | Track revision rounds per piece | Design & Video | Dileep, Rohit, Bhavya, Chaithanya | Client Edits | Self-Trigger | Each client edit | Per piece |  | DV-E1 |  |  |  | Admins (Abhista, Raviteja) | Rounds logged; flag if over 2 | Medium | No | No | Suggested
DV-X9 | Turnaround target: edit within 2 days of shoot | Design & Video | Dileep, Rohit | Video | Self-Trigger | After shoot | Per video |  | DV-V3 |  |  |  |  | Delivered on time | Medium | No | No | Suggested | Set your own target

## Summary
Team | Auto | Self-Trigger | Dependent | On Event | Total
Coordination | 10 | 4 | 10 | 1 | 25
Marketing | 30 | 6 | 9 | 3 | 48
Website | 10 | 4 | 11 | 0 | 25
Design & Video | 7 | 8 | 12 | 0 | 27
Total | 57 | 22 | 42 | 4 | 125

## People
Name | Team | Role | Main Work | Escalates To
Abhista | Management | Admin | Monitors everything; approves plans, audits, payments; receives escalations
Raviteja | Management | Admin | Monitors everything; approves plans, audits, payments; receives escalations
Shaheena | Coordination | Coordinator | Coordinator + Content Writer + Account Manager (assumed) | Abhista, Raviteja
Gouthami | Marketing | Member | GMB, social, ads, reports, onboarding | Shaheena
Ayesha | Marketing | Member | GMB, social, ads, reports, onboarding | Shaheena
Raghu | Website | Member | Website developer | Shaheena
Dileep | Design & Video | Member | Video shoots, edits, thumbnails | Shaheena
Rohit | Design & Video | Member | Posters, video edits, thumbnails | Shaheena
Bhavya | Design & Video | Member | Posters, animated videos (assumed) | Shaheena
Chaithanya | Design & Video | Member | Posters, animated videos, ad creatives | Shaheena

## Merged & Removed
Removed ID | Task | Now Covered By | Reason
MKT-M1 | Check clients' WhatsApp groups for queries | SHA-S1 | Client WhatsApp communication owned by Shaheena
MKT-M2 | Coordinate work to be done | SHA-S2 | Task assigning owned by Shaheena
MKT-M9 | Track videos | SHA-S5 + DV-C5 | Design team updates the video tracker, Shaheena monitors it
RAG-A1 | Update appointment booking system on Google | RAG-D3 | Duplicate of Raghu's daily Google Reserve slot

## How to Read
Column | Meaning
Task ID | Unique across all teams. Prefix = team: SHA Coordination, MKT Marketing, RAG Website, DV Design & Video.
Depends On (Same Team) | Task IDs that must be Done first. Comma = all of them. ¦ = any one of them.
Waiting On (Cross-Team) | Another team's task that delivers this task's input. Same comma / ¦ rules.
Trigger Type | Auto = scheduler creates it; Self-Trigger = unlocks after own previous step; Dependent = waits on someone else's input; On Event = created when something happens.
Per Client | Yes = create one instance per active client.
Needs Confirmation | Yes = based on an assumption; see Notes and the requirements doc.
Source | Where it came from: whiteboards, Added (needed by other teams), or Suggested (new best practice).